## Project Plan
Classic Circuit Calculator — Project Plan
Course | EECE2140
Project Leader (Iteration 2) | Brodie Newhouse
Team | Georgy Rached, Julia Terceros, Brodie Newhouse
Iteration 2 dates | Oct 18 – Oct 23
GitHub | https://github.com/brodienewhouse/Classic-Circuit-Calculator
Tasks
ID | Task | Menu | Owner | File / Function | Deliverable | Status | Notes
T1 | Switch cases / main menu (terminal) | 1 | Georgy | tasks.cpp / task1() | Working menu loop with switch cases that call functions | Done | Everything works as intended
T2 | Component classes | 2 | Brodie | tasks.cpp / task2() | Resistor and VoltageSource classes with constructors, getters and print() | In progress | Creating components
T3 | Series & parallel resistance functions | 3 | Julia | tasks.cpp / task3() | Functions that return equivalent resistance for series or parallel resistors | Not started | Stub in place; formulas planned
T4 | V, I, R, P calculator & unit tests | 4 | Julia | tasks.cpp / task4() | Ohm’s law / power solver for each component, plus AI-generated unit tests | Not started | Stub in place; depends on T2–T3
T5 | Front end & front-end integration | 5 | Georgy | tasks.cpp / task5() | User interface (built with Claude) connected to the C++ back end | Not started | Stub in place; starts when back end is done
T6 | Code review & bug fixes | 6 | Julia & Brodie | tasks.cpp / task6() | Reviewed code, fixed bugs, and a test run of every menu option | Not started | Stub in place; begins when all code is done
Progress
Done | 1
In progress | 1
Stub | 0
Not started | 4
% complete | 16.67%
Team
Member | Role · Tasks | This iteration
Brodie Newhouse | Project Leader · T2, T6 | Coordinated the team, ran the check-in, started the component classes
Georgy Rached | Developer · T1, T5 | Built the main menu and switch dispatch, set up task stubs
Julia Terceros | Developer · T3, T4, T6 | Planned the Circuit class and the series/parallel and V, I, R, P formulas
Status is a dropdown (Not started, Stub, In progress, Done) — the progress counts update automatically.